
TO:
Ashby
Awe
Berg
Bissen
Briggs
Bruno


Cigale
Dachik
Denny
DeRolf
Dorchester
Dreps


Gorman
Greiert
Greiling
Hadley
Hartmann
Kaspar


Kipp
Kramer
May
McKenzie
Micksch
Miskowski


Pokorney-Donelan
Putzer
Ribordy
Ritchie
Roslansky
Ruf


Salisbury
Salzmann
Schneider
Sloan-Miller
Sobol
Steele


Stickelmaier
Walz
Wilkens

FROM:  John Gerbig
Revised:  March 18, 2019
MAY  PLEDGE  2019 (119-026)

PRE-PRODUCTION SCHEDULE

                          (work order)
Mon,  4-29
Pledge hang / set / focus  (LD + Scenic + 2)
  9:30am  -    Noon


Pre-drive meeting / conf call  (Engel / 3-2542)
  1:30pm  -   2:00pm

Graphics Proofing  (2089 Vilas)
  2:00pm  -   2:30pm
Tue,  4-30
PCs / Laptops set  (Comp Svcs)
  8:00am  -   9:00am
119368


PCs / Laptops set  (Comp Svcs)
10:00am  -    Noon
119365


Bumpers edit / Omneon ingest  (Mary & Tom / Edit 9)
  1:00pm  -   2:00pm
119364


Engineering Memo meeting  (Ops Conf. Room)
  2:00pm  -   2:30pm
Wed,  5-1
Switcher set-up  (John / A Control)
  9:00am  - 11:00am
119361


Audio set-up & mic cable  (Audio Engineer)
10:00am  -    Noon
119362


Server set  (Video Engineer)
12:30pm  -   1:15pm
119363

Line-up  (Video, LD, TD, Line-up Op / 2 Cams)
  1:15pm  -   2:00pm



Set check  (Scenic, Video, LD, TD, 2 Cam Ops)
  2:00pm  -   2:30pm



Pre-records  (standard crew)
  2:30pm  -   3:00pm




Pledge lounge set-up  (Sup + 1, Prop Room)
  3:00pm  -   4:00pm

Thu,  5-2
Pre-records QC / FTP  (Dub Tape Engineer)
10:45am  -   Noon
119360
PRODUCTION SCHEDULE

                          (work order)

Sat,  5-4
Server set  (Video Engineer)
  5:30pm  -   6:15pm
119357

Line-up  (Video, Sup, Line-up Op, TD – 3 cams)
  6:15pm  -   6:45pm


May Pledge – Day 1  (Add 3rd Camera Op)
  6:45pm  -   9:15pm


(LIVE CAPTIONING)

Sun,  5-5
No live pledging Sunday?
Mon,  5-6
Server set  (Video Engineer)
  8:00am  -   8:30am
119356

Line-up  (Video, Sup, Line-up Op, TD)
  8:30am  -   9:00am



Taping Kids Pledge Breaks
  9:00am  -    Noon



No pledge Monday night
Tue,  5-7
Pledge set / lounge strike  (Sup + 3 + Audio Eng.)
  8:30am  - 11:30am

