November / December  Pledge  2020 (121-019) 
Bookings for ScheduAll
	Pledge set / focus
Monday, October 26       12:30 – 4:30pm

	Facilities:

Studio C

Studio B
	Personnel:

Lighting Director

Scenic Designer

Crew
	Record Stock:




Special Instructions:

LD + 1 crew + Scenic to check and tweak lighting for the upcoming Pledge records.
___________________________________________________________________________________
	Pledge mics / IFBs prep
Wed, October 28       9:00 – 11:30am

	Facilities:

Studio C

Studio B


	Personnel:

Audio Engineer
	Record Stock:




Special Instructions:

Audio engineer to make sure all mics and IFBs are in order for the upcoming Pledge records.  Update the Pledge scene files on the audio console.

___________________________________________________________________________________ 

	Pledge Server Set-up
Mon, November 2     9:00 – 10:00am

	Facilities:

“A” Control

HD Server  VT #50

HD Server  VT #51

HD Server  VT #52
MediaNXS  VT #55

MediaNXS  VT #56

MediaNXS  VT #57

Loop Player  VT #91

Loop Player  VT #92
	Personnel:

Video Engineer


	Record Stock:




Special Instructions:

* Prepare Spectrum X and MediaNXS  VT`s for Pledge.  Set to Pledge directory.

* Run Pledge salvo and make all necessary patches. Verify signal paths are correct.

* Make sure Ross switcher is turned on and powered up.

___________________________________________________________________________________
	Pledge switcher set-up
Mon, November 2     10:00am – 2:00pm

	Facilities:

“A” Control

HD Server  VT #50

HD Server  VT #51

HD Server  VT #52
MediaNXS  VT #55

MediaNXS  VT #56

MediaNXS  VT #57

Loop Player  VT #91

Loop Player  VT #92
	Personnel:

Technical Director (Rachael)
	Record Stock:




Special Instructions:

Rachael to set up the Ross switcher for the upcoming drive.
_______________________________________________________________________________

	Pledge line-up
Mon, November 2     2:00 – 3:00pm

	Facilities:

Studio Camera Line Up

Studio C

Studio B
“A” Control

Edit 1

HDC 900 Sony 1

HSC 100 Sony 6
CC Encoder / AUX30
	Personnel:

Video Engineer

Camera Operator

Lighting Director / Production Sup
Switcher  (Rachael?)

	Record Stock:




Special Instructions:

Line-up for upcoming Pledge drive set check.  Video engineer will check and adjust color-correction for both on-set monitors.

___________________________________________________________________________________
	Pledge set check
Mon, November 2     3:00 – 4:00pm

	Facilities:

Studio C

Studio B

“A” Control

Edit 1

UPlace Central

VO Booth

HDC 900 Sony 1

HSC 100 Sony 6

CC Encoder / AUX30

HD Server  VT #50

HD Server  VT #51

HD Server  VT #52
MediaNXS  VT #55

MediaNXS  VT #56

MediaNXS  VT #57

Loop Player  VT #91

Loop Player  VT #92
	Personnel:

Video Engineer
Lighting Director / Production Sup
Camera Operator
Switcher  (Rachael?)
	Record Stock:




Special Instructions:

Check sets and lighting for upcoming drive.  Check loops and animations in on-set monitor.  Check lower-third animation.  Check Challenge Clock and crawls.  Check all switcher functions.
 ___________________________________________________________________________________

	Pledge line-up
Tue, November 3     9:30 – 10:00am

	Facilities:

Studio Camera Line Up

Studio C

Studio B

“A” Control

Edit 1

HDC 900 Sony 1

HSC 100 Sony 6

CC Encoder / AUX30
	Personnel:

Video Engineer

Camera Operator

Lighting Director / Production Sup

Switcher

	Record Stock:




Special Instructions:

Line-up for upcoming Pledge breaks record.  Video engineer will check and adjust color-correction for both on-set monitors.

___________________________________________________________________________________
	Pledge breaks record
Tues, November 3   10:00am – 4:00pm

	Facilities:

Studio C

Studio B

“A” Control

Edit 1

UPlace Central

VO Booth

HDC 900 Sony 1

HSC 100 Sony 6

CC Encoder / AUX30

HD Server  VT #50

HD Server  VT #51

HD Server  VT #52
MediaNXS  VT #55

MediaNXS  VT #56

MediaNXS  VT #57

Loop Player  VT #91

Loop Player  VT #92
	Personnel:

Video Engineer

Audio Engineer

Production Sup

Camera Operator

Switcher
	Record Stock:




Special Instructions:

Record breaks for the upcoming drive, on MediaNXS (VTs 59-60-61).

 ___________________________________________________________________________________
	Pledge edit
Thurs, November 5     9:30am – 3:30pm 

	Facilities:

Edit Suite

	Personnel:

Editor (Tom Micksch?)

	Record Stock:




Special Instructions:

Prep pledge goal bumper.  Edit easel segment roll-ins for use in future break records.  Any other editing, as needed, for upcoming drive.
___________________________________________________________________________________
	Pledge line-up
Mon, November 9     9:30 – 10:00am

	Facilities:

Studio Camera Line Up

Studio C

Studio B

“A” Control

Edit 1

HDC 900 Sony 1

HSC 100 Sony 6

CC Encoder / AUX30
	Personnel:

Video Engineer

Camera Operator

Lighting Director / Production Sup

Switcher

	Record Stock:




Special Instructions:

Line-up for upcoming Pledge breaks record.  Video engineer will check and adjust color-correction for both on-set monitors.

___________________________________________________________________________________
	Pledge breaks record
Mon, November 9   10:00am – 4:00pm

	Facilities:

Studio C

Studio B

“A” Control

Edit 1

UPlace Central

VO Booth

HDC 900 Sony 1

HSC 100 Sony 6

CC Encoder / AUX30

HD Server  VT #50

HD Server  VT #51

HD Server  VT #52
MediaNXS  VT #55

MediaNXS  VT #56

MediaNXS  VT #57

Loop Player  VT #91

Loop Player  VT #92
	Personnel:

Video Engineer

Audio Engineer

Production Sup

Camera Operator

Switcher
	Record Stock:




Special Instructions:

Record breaks for the upcoming drive, on MediaNXS (VTs 59-60-61).

 ___________________________________________________________________________________
	Pledge edit
Thurs, November 12     9:30am – 12:30pm 

	Facilities:

Edit Suite

	Personnel:

Editor (Tom Micksch?)

	Record Stock:




Special Instructions:

Do any additional editing for pledge breaks.
___________________________________________________________________________________
	Pledge breaks QC / FTP
Wed, November 18    9:00am – Noon         

	Facilities:

Dub Tape

HD Server VT #49
	Personnel:

Dub Tape Engineer
	Record Stock:




Special Instructions:

SpectrumX File:  TBD

SpectrumX Folder:  Pledge

Check for correct video levels, audio phase and dialnorm levels, lip sync, closed captioning accuracy and synchronicity, and no file stuttering or freezing.

Please mark the breaks approved on the Engineering MXF QC page:

<<http://144.92.195.40/Broadcast/MXF/EngQC>>

Please initial and date (YYYYMMDD) the breaks approved on the Program File Transfer Google Doc 

(under “Vilas Passed QC”).

___________________________________________________________________________________
	Pledge strike
Tuesday, December 15    8:30am – Noon   

	Facilities:

Studio C

	Personnel:

Production Supervisor
Audio Engineer
2 Crew
	Record Stock:




Special Instructions:

Strike pledge set.
